## User Guide
User Guide for Award Management Checklists
Disclaimer
There are two checklists to assist with managing the award through its post-award lifecyle: 1) During Award and 2) During Closeout.
The "During Award" checklist can be used once a project is awarded and up to 90-days prior to the award/account end date.
The "During Closeout" checklist can be used 90-days prior to the award/account end date and throughout the closeout of the award/account in GMAS and the GL.
The checklists are NOT required by OSP, but can be incorporated into a school or department's local procedures to assist with managing awards.
The activities listed on each checklist should be performed on a MONTHLY basis, unless another frequency is specified.
Each checklist provides a general framework of the responsibilities required with managing a sponsored research award and can be used to supplement a school or department's local procedures.
The checklists are not meant to be an exhaustive list of activities, since each award is different and may require unique and varying levels of management throughout the lifecycle of the project.
These checklists can be downloaded and customized to assist with the management of specific award terms and conditions.
When relevant, links to associated policies and guidance are included below the activities on the checklists.
To ensure sponsored accounts are closed on a timely basis, the "During Closeout" checklist can be used as a resource when reviewing year logic accounts reaching a budget
period end date, or when reviewing task logic accounts reaching a project period end date.
Frequently Asked Questions
1. Why is the checklist important?
Effective grant management is a cornerstone for ensuring compliance with sponsor policies and award terms and conditions. These checklist outline the most common areas that require oversight
and monitoring throughout the award.
2. How should the checklists be used?
The checklists provide a centralized method for tracking common post-award activities that occur during an award and closeout. It is recommended that checklists be reviewed monthly, but are not required by OSP.
Local units can incorporate the checklists into their local procedures to provide standardization and consistency with the oversight of sponsored awards. The checklists can also be very useful when
onboarding new grant managers or those new to managing sponsored awards.
3. What should I do with the checklists?
Checklists can be saved locally for others to access. These checklists can be especially useful when training and onboarding new staff; providing them with a resource to reference throughout the award.
The checklists should not be uploaded to GMAS or submitted to OSP. The checklists are also useful when transitioning portfolios, since they provide a summary of the monitoring that has already
taken place.
4. Who do I go to if I have question about the checklist?
Relevant links to policy and guidance are included throughout the checklist. If there are specific questions about checklist activities, users should check with their local manager to understand the local
procedures. If there are questions about University policy, guidance, and business process, the OSP Financial Analyst or School Central Research Administration Office can provide additional support.
5. What about pre-award activities (i.e. disclosures, IP, etc.)?
The primary focus of these checklists is on the post-award financial management of an award, including the closeout activities.
6. Why don't the checklists include a "critical time" to perform each activity?
All activities on the "During Award" checklist should be performed monthly, unless noted with a different frequency. In addition, a "Higher Priority" column helps to identify activities that should never be
skipped. Activities on the "During Closeout" checklist should be performed monthly, beginning 90-days prior to the end date of the award.
7. What's the difference between the OSP Compliance Checklist and the Award Management Checklist ? Are both required?
The OSP Compliance Checklist is coordinated by OSP and must be reviewed and confirmed by the DLLMU in order for OSP to complete a scheduled financial deliverable. The Award Management Checklist is not
required by OSP, but it can be used by DLLMUs to assist with the management and closeout of awards. The Award Management Checklist can be customized by the DLLMU based on local procedures and/or
sponsor terms and conditions.
8. What is a DLLMU?
The Department Local Level Managing Unit (DLLMU) is the terminology designated by the Operations and Policy Committee (OPC) when referring to departments, center, smaller schools, and local units
within Harvard that are responsible for managing sponsored awards. The roles associated with the DLLMU can include, but are not limited, grant managers, grant administrators, lab directors, finance
managers, grants specialists, associate directors of finance and administration, etc.
Middlesex 017
Suffolk 025

## During Award
Award Management Checklist - During Award
Harvard Fund Number: |  |  | Obligated Dates:
Sponsor Name: |  |  | Anticipated Dates:
Principal Investigator: |  |  | OSP Contact:
Award Number: |  |  | Pre-Award Contact:
Prime Award Number: |  |  | Date:
DISCLAIMER
This checklist outlines activities to manage "during the award" and should be performed on a MONTHLY basis unless a different frequency is noted. Higher priority activities are noted with an asterisk (*).
If an account is approaching 90-days before its end date, please reference the "During Closeout" checklist.
This checklist provides a general framework of the responsibilities required to manage sponsored research awards and can be used to supplement any local procedures. It is NOT REQUIRED BY OSP.
RESPONSIBILITY LEGEND ** | DLLMU = Department/Local Level Managing Unit; OSP RF = Office for Sponsored Programs Research Finance; PI = Principal Investigator, Pre-Award = Central Pre-Award Office
Topic | Checklist Activity NOTE: higher priority activities are noted with an asterisk (*) | * Higher Priority | ** Primary (And Secondary) Responsibility | Tracking and Notes (use these fields to record the completion of activities and any relevant notes throughout the award)
Award Balance | Review award balances (overspent, underspent, projected spending rate through award end date). | * | DLLMU
Award Balance | Review the HART Committed Funds (or PI Dashboard) report to check for open Purchase Orders. | * | DLLMU
HART Wiki: Committed Funds Report
Award Balance | Check in with PI and research team about progress, and remaining outstanding purchases. |  | DLLMU (PI)
Award Balance | Remind PI and research team to submit any outstanding reimbursements for travel or other expenses. |  | PI (DLLMU)
Award Balance | If applicable: Follow up on outstanding subcontract invoices throughout the subcontract period of performance. Obtain PI approval of invoices and ensure all subcontract transactions are posted in the GL using the appropriate object codes (8190-8193). |  | DLLMU
OSP Website: Budget Expense Object Codes - Subcontract Object Codes
Award Balance | If applicable: Follow up with vendors/suppliers/consultants/"outgoing" billing agreements on outstanding invoices throughout period of performance. |  | DLLMU
Award Balance | If applicable: Consult with the PI to determine if a no-cost extension (NCE) is needed, particularly when account is underspent. |  | PI (DLLMU)
Personnel | Confirm personnel allocations with PI and update coding for salary (and tuition) as necessary. If applicable: For any departing personnel, obtain manual effort certifications or fill out a proxy form. | * | PI (DLLMU)
GL Adjustments | Remove any over-expenditures or unallowable charges as soon as they are discovered. | * | DLLMU
GL Adjustments | Review GMAS Transaction Monitoring to clear flagged transactions. | * | DLLMU (OSP RF)
Overview: GMAS Transaction Monitoring Dashboard
GL Adjustments | Correct any Invalid Code Combinations (ICCs) within 90 days of posting. | * | DLLMU (OSP RF)
HART Wiki: Invalid Code Combinations Report
GL Adjustments | Review recurring charges and any changes to allocation methodologies. Ensure an allocation methodology is documented. NOTE: this activity should be monitored at least quarterly, but should be monitored any time a change is made to routine allocations or the allocation methodology. |  | DLLMU
Guidance: Cost Allocation Methodologies
GL Adjustments | If applicable: correct expense object codes in the general ledger if the cumulative balance is a credit/negative, (e.g. more has been credited to an expense object code than was originally posted). Note: some object codes such as vacation fringe and write-offs (7761 and 7765) CAN have a negative balance. |  | DLLMU
Financial Reporting | For interim financial deliverables, review and approve OSP Compliance Checklist within five business days of receiving a checklist email from OSP. NOTE: this activity is based on the financial deliverable schedule for an award. |  | DLLMU (OSP RF)
Financial Reporting | Review the GMAS Financial Deliverable Dashboard or the HART Scheduled Reports to identify any financial reports or invoices that are due to the sponsor and coordinate the completion and submission with OSP. |  | OSP RF (DLLMU)
Overview: GMAS Financial Deliverable Dashboard
Financial Reporting | Work with OSP Financial Analyst to produce and submit any financial reports or invoices. |  | OSP RF (DLLMU)
Reconciliation | Ensure spending is accurate and aligned with sponsor budgets and award terms and conditions. | * | DLLMU
Reconciliation | OSP will assist with Accounts Receivable collections and follow-up with department if needed. |  | OSP RF (DLLMU)
Overview: Accounts Receivable
Reconciliation | If applicable: Review companion accounts to ensure cost share requirements are being met throughout the award. |  | DLLMU (OSP RF)
Policy: Cost Sharing - Appendix B Companion Account Coding
Reconciliation | If applicable: When cost share is required, ensure cost share commitments are recorded appropriately in the GL or tracked/documented for cost share that cannot be recorded in the GL. When required, provide OSP with cost share support for reporting to sponsor. |  | DLLMU (OSP RF)
Policy: Cost Share
Reconciliation | If applicable: Review program income and work with OSP to reconcile. NOTE: a separate Program Income subactivity must be set up in GMAS if program income is associated with the award. |  | DLLMU (OSP RF)
Guidance: Program Income
Reconciliation | If applicable: Review Participant Support Costs (PSC). NOTE: a separate PSC subactivity must be set up in GMAS if PSC is allowable. |  | DDLMU (OSP)
Guidance: Participant Support Costs
Reconciliation | If applicable: Review sponsor terms and conditions to identify if any interest earned can be retained (and offset project expenditures). |  | DLLMU (OSP RF)
Reconciliation | If applicable: Confirm if currency fluctuations would require PI to cover any overruns or how to deal with remaining balances. |  | DLLMU (OSP RF)
Guidance: Awards Paid In Foreign Currency
GMAS Project Information | Review open GMAS requests and pending revisions. |  | DLLMU (Pre-Award)
GMAS Project Information | If applicable: Ensure approvals in GMAS have been cleared and monitor project changes for international collaborations and activities (ICA) (e.g. IACUC, IRB, ICA, etc.). |  | DLLMU (Pre-Award)
Overview: Approvals
Non-Financial Reporting | Remind PI and research team of technical and non-financial reports required formats and due date. Maintain a schedule for tracking programmatic due dates for RPPRs, project deliverables and milestones, progress reports, etc. Note: GMAS has functionality to schedule and record non-financial reports. |  | PI (DLLMU)
Non-Financial Reporting | Confirm with PI that technical, progress, invention, patent or property reports have been submitted. It is strongly encouraged to upload/save the non-financial reports in GMAS. NOTE: NIH RPPRs are routed through GMAS for review by the central submitting office for submission. |  | PI (DLLMU)
Non-Financial Reporting | If applicable: In the event a sponsor reaches out for an audit, site visit, desk review, etc., please reach out to an OSP Manager or Financial Analyst. OSP is the primary contact for any audit requests. |  | OSP
Overview: Auditing
Additional Comments
Middlesex 017
Suffolk 025

## During Closeout
Award Management Checklist - During Closeout
Harvard Fund Number: |  | Obligated Dates:
Sponsor Name: |  | Anticipated Dates:
Principal Investigator: |  | OSP Contact:
Award Number: |  | Pre-Award Contact:
Prime Award Number: |  | Date:
DISCLAIMER
This checklist is specific to "closeout" and includes monthly activities that should be performed 90-days before the end date and throughout closeout. There is a separate checklist of activities to monitor "during the award".
This checklist provides a general framework of the responsibilities required to manage sponsored research awards and can be used to supplement any local procedures. It is NOT REQUIRED BY OSP.
RESPONSIBILITY LEGEND ** | DLLMU = Department/Local Level Managing Unit; OSP RF = Office for Sponsored Programs Research Finance; PI = Principal Investigator, Pre-Award = Central Pre-Award Office
Topic | Checklist Activity NOTE: Perform these activities monthly, beginning 90-days before the end date and throughout closeout | Primary (and Secondary) Responsibility ** | Tracking and Notes (use these fields to record the completion of activities and any relevant notes throughout the award)
Award Balance | Check in with PI and research team about progress, and remaining outstanding purchases. | DLLMU
Award Balance | Remind PI and research team to submit any outstanding reimbursements for travel or other expenses. | PI (DLLMU)
Award Balance | Review the HART Committed Funds report (or PI Dashboard) to check for open Purchase Orders. | DLLMU
HART Wiki: Committed Funds
Award Balance | If applicable: For underspent accounts, review and discuss award terms for carryforward restrictions with PI if a renewal is anticipated. Submit an NCE Request in GMAS and continue to review the status of any pending NCE requests until approved/processed. | DLLMU (PI)
Award Balance | If applicable: Follow up on outstanding subcontract invoices throughout the subcontract period of performance, including a Final Invoice. Obtain PI approval. Ensure all subcontract transactions are posted in the GL using the appropriate object codes (8190-8192). Please note: Any advance subcontract payments posted to 8193 must be reconciled by transferring them to the 8190-8192 range or removing any advance payments that were not spent, requesting a refund from the subawardee. | DLLMU
OSP Website: Budget Expense Object Codes - Subcontract Object Codes
Award Balance | If applicable: Follow up with vendors/suppliers/consultants/"outgoing" billing agreements on outstanding invoices throughout period of performance. | DLLMU
Personnel | Review personnel allocations with PI and update the costing to move personnel after award end. | PI (DLLMU)
Personnel | If applicable: For any departing personnel, obtain manual effort certifications or fill out a proxy form. | DLLMU
Policy: Effort Reporting
Personnel | If applicable: Ensure that current tuition charges align with salary and that upcoming tuition charges will not be paid from the award. | DLLMU
GL Adjustments | Review recurring charges and any changes to allocation methodologies. Ensure an allocation methodology is documented. NOTE: this activity does not have to be monitored monthly, but should be monitored any time a change is made to routine allocations or the allocation methodology. | DLLMU
Guidance: Cost Allocation Methodoloy
GL Adjustments | Review GMAS Transaction Monitoring. All flagged transactions must be cleared prior to confirming the Compliance Checklist with OSP. | DLLMU (OSP RF)
GL Adjustments | Overview: GMAS Transaction Monitoring Dashboard
GL Adjustments | If applicable: correct expense object codes in the general ledger if the cumulative balance is a credit/negative, (e.g. more has been credited to an expense object code than was originally posted). Note: some object codes such as vacation fringe CAN have a negative balance | DLLMU
GL Adjustments | If applicable: Work with your school equipment manager or finance office to ensure equipment Works in Progress (WIPs) are placed in service or disposed prior to account disabling. | DLLMU
GL Adjustments | If applicable: ensure that the first $25k of any subawards has been charged to object code 8190, and any amount above that to a different subaward object code. NOTE: The correct object codes must be used even if the IDC is 0%. | DLLMU
Financial Reporting | Review and approve OSP Compliance Checklist, including any final figures (amount for closeout in the GL) within five business days of receiving the checklist email from OSP. NOTE: The timely confirmation of final figures directly impacts the letter of credit drawdowns. | DLLMU (OSP RF)
Financial Reporting | Review the GMAS Financial Deliverable Dashboard or HART Scheduled Reports to identify any financial reports or invoices that are due to the sponsor and coordinate the completion and submission with OSP, including the Assignment and Release Forms. | OSP RF (DLLMU)
Overview: GMAS Financial Deliverable Dashboard
Financial Reporting | Ensure the final figure reported to the sponsor matches total expenditures posted in the GL. | OSP RF (DLLMU)
Financial Reporting | Verify in GMAS that all financial reports have been submitted. | OSP RF
Recurring Charges | Review recurring charges on the account such as service center, p-card, corporate card, animal and other charges to make sure they will not post after account ends (e.g. monthly service fees such as labs, document management, other data access systems, etc.). | DLLMU
Recurring Charges | Request/change coding for service centers, p-card, corporate card, animal and other routine allocations to ensure they are not posting after account end date. | DLLMU
Recurring Charges | If applicable: Review program income if applicable and work with OSP to reconcile. NOTE: a separate Program Income subactivity must be set up in GMAS if program income is associated with the award. | DLLMU (OSP RF)
Guidance: Program Income
Recurring Charges | If applicable: Review Participant Support Costs (PSC). NOTE: a separate PSC subactivity must be set up in GMAS if PSC is allowable. | DDLMU (OSP)
Guidance: Participant Support Costs
Reconciliation | Ensure all expected or outstanding expenses have hit the award. | DLLMU (OSP RF)
Reconciliation | Confirm with your OSP Financial Analyst that the indirect costs/overhead has been booked correctly. | DLLMU (OSP RF)
Reconciliation | Inform project team members that the account string will be disabled after the award end date. | DLLMU
Reconciliation | Continue to monitor accounts after the end date and resolve any late charges posted after the final figure is confirmed. Continue to monitor accounts until they are disabled in the GL. NOTE: the automated disabling occurs 90-days after the account end date, but if an account is reconciled before then, please reach out to the OSP Financial Analyst and they can queue the account to disable before that. | DLLMU (OSP RF)
Reconciliation | If applicable: Coordinate with departments on any Part-of accounts. Confirm they are in process of final reconciliation and closeout or aware of NCE (if applicable). | DLLMU
Reconciliation | If applicable: Reconcile companion accounts or reach out to your FA in OSP to assist with any reconciling entries to allow sponsored accounts to disable. | DLLMU (OSP RF)
Policy: Cost Sharing
Reconciliation | If applicable: When cost share is required, ensure cost share commitments are recorded appropriately in the GL or tracked/documented for cost share that cannot be recorded in the GL. When required, provide OSP with cost share support for reporting to sponsor. By award end, all cost share must be charged correctly in the GL companion and/or supporting documentation provided to OSP to confirm cost share commitments have been met. | DLLMU (OSP RF)
Policy: Cost Sharing - Appendix B Companion Account Coding
Reconciliation | If applicable: Review sponsor terms and conditions to identify whether any interest earned and not spent during the course of the award can be either transferred to a discretionary account or must be returned to sponsor. Contact OSP Research Finance if the terms are not clear. | DLLMU (OSP RF)
Reconciliation | If applicable: Complete fixed price balance transfer form and email to your school level representative for approval and coordination with OSP for transfer. | DLLMU (OSP RF)
Guidance: Fixed Price Sponsored Awards
GMAS Project Information | If applicable: Ensure approvals in GMAS have been cleared (e.g. IACUC, IRB, ICA, fCOI, etc.). Note: All open approvals must be cleared in order for the segment to be closed. | DLLMU (Pre-Award)
Overview: Approvals
GMAS Project Information | If applicable: Request an At-Risk account if additional funding is anticipated and/or if delays are expected with negotiating the next increment of funding. | DLLMU
Overview: At-Risk Accounts
Non-Financial Reporting | Confirm with PI that technical, progress, invention, patent or final property reports have been submitted. It is strongly encouraged to upload/save the non-financial reports in GMAS. NOTE: NIH RPPRs are routed through GMAS for review by the central submitting office for submission. Note: GMAS has functionality to schedule and record non-financial reports. | PI (DLLMU)
Non-Financial Reporting | Request copies of technical reports for records and/or email confirming submission to sponsor. It is strongly encouraged to upload/save the non-financial reports in GMAS. | PI (DLLMU)
Non-Financial Reporting | If applicable: In the event a sponsor reaches out for an audit, site visit, desk review, etc., please reach out to an OSP Manager or Financial Analyst. OSP is the primary contact for any audit requests. | OSP DLLMU
Overview: Auditing
Additional Comments
Middlesex 017
Suffolk 025